## Sheet1
Task | Task description | Team members |  |  | Status
|  | Cojocaru Ionuţ | Deaconescu Andrei | Stănescu Mihai
1.1.1 | user and password | 0 | 1 | 0 | Done
1.1.2 | password hidding | 0 | 1 | 0 | Done
1.1.3 | authentification confirmation | 0 | 1 | 0 | Done
1.1.4 | log in redirect to home | 0 | 1 | 0 | Done
1.2.1 | register page data fields | 0 | 0 | 1 | Done
1.2.2 | password protection | 0 | 0 | 1 | Done
1.2.3 | data validation | 0 | 0 | 1 | Done
1.2.4 | register redirect to log in | 0 | 0 | 1 | Done
1.3.1 | log out process | 1 | 0 | 0 | Done
1.4.1 | email address field | 1 | 0 | 0 | Done
1.4.2 | email validation | 1 | 0 | 0 | Done
1.4.3 | password reset | 1 | 0 | 0 | Done
2.1 | departments name list | 0 | 1 | 0 | Done
2.2 | add department | 2 | 0 | 0 | In progress
2.3 | modify department | 2 | 0 | 0 | In progress
2.4 | delete department | 1 | 0 | 0 | In progress
2.5 | departments graphical representation | 0 | 3 | 0 | Done
2.6 | relations between departments | 0 | 2 | 0 | Done
2.7 | add department personnel information | 0 | 0 | 2 | In progress
2.8 | add department personnel relations | 0 | 0 | 2 | In progress
2.9 | view department personnel information | 0 | 0 | 1 | Done
2.10 | view department personnel relations | 0 | 0 | 1 | Done
2.11 | store chart | 0 | 2 | 0 | Done
3.1 | audience schedule planning | 2 | 0 | 0 | Done
3.2 | multiple user chat | 4 | 0 | 0 | Done
3.3 | mayor audience report | 2 | 0 | 0 | Done
3.4 | audience request | 0 | 0 | 2 | Done
3.5 | audience request response | 0 | 0 | 2 | Done
3.6 | chat initiation procedure | 0 | 0 | 3 | Done
4.1 | documents storage | 0 | 3 | 0 | Done
4.2 | documents categories | 0 | 1 | 0 | In progress
4.3 | database documents search | 0 | 2 | 0 | Done
4.4 | search criteria | 0 | 1 | 0 | Done
4.5 | scanning documents facility | 2 | 0 | 0 | In progress
4.6 | printing documents facility | 2 | 0 | 0 | Done
4.7 | document modify stamp | 1 | 0 | 0 | In progress
5.1 | client intuitive interface | 0 | 0 | 3 | Done
5.2 | client user-friendly interface | 0 | 0 | 4 | Done
5.3 | admin intutive interface | 3 | 0 | 0 | Done
5.4 | admin user-friendly interface | 4 | 0 | 0 | Done
5.5 | text icons | 0 | 2 | 0 | Done
5.6 | drop-down list | 0 | 3 | 0 | Done
5.7 | define fonts types | 1 | 0 | 0 | Done
5.8 | define font sizes | 1 | 0 | 0 | Done
5.9 | user name display | 0 | 0 | 1 | Done
6.1 | database store data | 0 | 2 | 0 | In progress
6.2 | database modify data | 0 | 2 | 0 | In progress
6.3 | database delete data | 0 | 1 | 0 | In progress
6.4 | database retrieve data | 0 | 2 | 0 | Done
6.5 | database modify structure | 0 | 0 | 3 | In progress
6.6 | user rights administration | 0 | 0 | 2 | Done
6.7 | data modification log | 0 | 0 | 1 | In progress
Total hours |  | 31 | 31 | 31

## Sheet2
Done
In progress
Not started